## Slide 1
MYDAWA · BOARD BRIEFING
Recovery Programme:
What Happened, What We're Doing,
How You'll Know It's Working
A board-level reference for the next six months.
Prepared for the Group COO and the Board · Period of recovery: Months 1 – 6
Use this document to: approve the plan, run monthly reviews, decide when to escalate.

## Slide 2
WHAT HAPPENED
The story in five sentences
If you read nothing else in this document, read this slide.
1
Revenue grew 20% in 2024, then fell 5% in 2025.
We had our best year ever in 2024 and our first contraction in 2025.
2
Customer count looks roughly stable. The story is in how we got there.
We acquired about 44,000 new customers in 2023, 26,000 in 2024, and 22,000 in 2025. New-customer acquisition has roughly halved.
3
Our most loyal customers — about 19,000 of them — held the line through 2024.
These customers buy almost monthly and deliver around two-thirds of our revenue. They held us up while acquisition slowed.
4
Then in late 2025, the website checkout broke.
Customers reach our site, choose products, add them to their cart — and most cannot complete the purchase. Cart-to-order conversion fell from 22% to 7%.
5
Loyal customers can no longer compensate. The contraction has surfaced.
Three things broke at once: site traffic, conversion rate, and most acutely the checkout step. The recovery plan addresses all three.
MYDAWA · BOARD BRIEFING · RECOVERY PROGRAMME
02

## Slide 3
WHY IT MATTERS
What the numbers say — without the spreadsheet
Three numbers that frame the size of the problem and the size of the recovery.
−5.5%
REVENUE FELL IN 2025
After a +20% year. The first time MYDAWA has not grown.
7%
CHECKOUT CONVERSION TODAY
Was 22% historically. Three out of every four would-be customers cannot complete their purchase.
KES 130M+
RECOVERY OPPORTUNITY
What returning the funnel and acquisition to 2024 levels would add back to annual revenue.
Bottom line: This is fixable. The biggest leak is also the easiest to fix.
MYDAWA · BOARD BRIEFING · RECOVERY PROGRAMME
03

## Slide 4
THE RECOVERY PLAN
Six months in three phases
Each phase has a clear job. We do not move to the next phase until the current one has done its job.
MONTH 1
STOP THE BLEEDING
Fix the checkout. Prove our diagnosis is right.
WHAT WE DO
Two teams work on one priority: get the website checkout working again, and clean up the data we use to measure it.
HOW YOU KNOW IT WORKED
Cart-to-order conversion back above 15% by end of month.
MONTHS 2 – 4
REBUILD
Bring back acquisition. Defend our best customers. Clean the foundations.
WHAT WE DO
Marketing rebuilds new-customer acquisition. Site experience improves. We reactivate dormant customers. We fix data and product hygiene.
HOW YOU KNOW IT WORKED
Monthly revenue back at KES 32M for two months running.
MONTHS 5 – 6
PROVE IT'S DURABLE
Make sure the gain is real, not a bounce. Hand back to BAU.
WHAT WE DO
No new actions. We document what worked, watch the numbers hold, and transition the programme back to functional teams.
HOW YOU KNOW IT WORKED
Two consecutive months at target. Programme closes.
MYDAWA · BOARD BRIEFING · RECOVERY PROGRAMME
04

## Slide 5
WHAT GETS DONE, AND WHO DOES IT
Eight workstreams, named owners, single accountabilities
No co-ownership. Each workstream has one named accountable person. The COO escalates if any cannot deliver.
#
WHAT
WHY IT MATTERS
OWNER
BY
1
Fix the checkout
Largest leak. 7% conversion has to return to 18%+.
Head of Ecommerce Ops & Fulfilment
Month 1
2
Trustable funnel data
We can't manage what we can't measure cleanly.
Head of Growth
Month 1
3
Marketing spend rebuild
Acquisition halved; we need the spend story.
Head of Growth (Group CFO supporting)
Month 2
4
Bring back lapsed customers
45,000 customers bought once and never returned. Reactivate 10%.
Head of Customer Experience
Month 3
5
Better website experience
Conversion rate fell 30%. Get it back to 2%.
Head of Ecommerce Ops & Fulfilment
Month 3
6
Defend our best customers
19,000 loyalists give us 65% of revenue. Don't lose them.
Head of Medical (Supply Chain supporting)
Month 4
7
Fix our product data
30% of products carry no proper category. Every report is partly blind.
Head of Supply Chain
Month 3
8
Clean the catalogue
2,000 products haven't sold in a year. Decide: keep, drop, or order-to-demand.
Head of Supply Chain (Retail Ops supporting)
Month 4
MYDAWA · BOARD BRIEFING · RECOVERY PROGRAMME
05

## Slide 6
HOW YOU'LL KNOW IT'S WORKING
Three layers of measurement — for three audiences
The board looks at one number. The COO looks at three. Each owner looks at one. Nobody is asked to monitor everything.
FOR THE BOARD · ONE NUMBER · REVIEWED MONTHLY
Monthly revenue
Today: KES 28.5M / month. Target: KES 32M+ / month, sustained for two months running by Month 6.
1
FOR THE COO · THREE EARLY-WARNING SIGNALS · REVIEWED WEEKLY
These move before revenue does. If they aren't moving, neither will revenue.
Checkout conversion
7%
→
≥ 18%
Daily for 30d
Site conversion rate
1.3%
→
≥ 2.0%
Weekly
New customers / month
~2,250
→
≥ 2,800
Weekly
3
FOR EACH OWNER · ONE NUMBER PER WORKSTREAM · REVIEWED WEEKLY
Each owner has a single number that proves their work is moving. They report it weekly.
Examples: checkout pass-rate · funnel data coverage · marketing spend by channel · reactivated customers · CRO test win-rate · loyalty cohort retention · classified products % · cleared dormant SKUs.
8
MYDAWA · BOARD BRIEFING · RECOVERY PROGRAMME
06

## Slide 7
THE KPI CONTRACT
Eight workstreams, eight KPIs — baseline, target, cadence
Every metric written in the same form. No target without baseline. No baseline without a review rhythm.
#
KPI
BASELINE
TARGET
CADENCE
A1
Cart → Order conversion
7.1% (Q1 '26)
≥ 18%
Daily for 30d, then weekly
A2
Funnel telemetry coverage
~70% (Nov-Dec gaps)
100% reconciled
Weekly
A3
Monthly new-customer acquisition
~50% of 2023 peak
≥ 80% of 2023 peak
Weekly
A4
One-and-done customers reactivated
0 of 45,000 lapsed
≥ 4,500 (10%)
Bi-weekly
A5
Site conversion rate
1.4% (was 2.0%)
≥ 2.0%
Weekly
A6
Champion 90-day retention rate
Locked Week 1
+5pp on baseline
Monthly
A7
SKU classification completeness
70% (4,555 missing)
100%
Weekly milestone
A8
Dormant SKU count (12-mo no sale)
2,036
< 800
Monthly
A6 baseline is locked in Week 1 — Champion 90-day retention has not been measured before. The first measurement becomes the baseline; the +5pp target attaches to it.
MYDAWA · BOARD BRIEFING · RECOVERY PROGRAMME
07

## Slide 8
THE CADENCE
Who meets when, what they decide
A recovery only works if the rhythm of conversation matches the rhythm of the data. This is that rhythm.
DAILY
Workstream owners
WHAT HAPPENS
First 30 days only. 15-minute stand-up. Owners share what moved, what's blocked. The COO drops in unannounced.
WHAT GETS DECIDED
Unblock. Reassign capacity. Escalate within hours, not days.
WEEKLY
COO + lead owners
WHAT HAPPENS
60 minutes, every Monday. Three lead KPIs reviewed against target. Each owner reports their one operational KPI.
WHAT GETS DECIDED
Stay the course, accelerate, or pivot. Reallocate budget within the programme.
MONTHLY
Board + COO
WHAT HAPPENS
90 minutes. Headline KPI (revenue) plus the three lead indicators. One slide per phase showing where we are vs the plan.
WHAT GETS DECIDED
Phase advancement. Approval of new budget asks. Whether stop conditions have triggered.
QUARTERLY
Full executive team
WHAT HAPPENS
Half-day. Programme-level review. What worked, what didn't, what's next quarter's emphasis. Owners present in their own voice.
WHAT GETS DECIDED
Plan adjustments. Programme close-down (Month 6). Hand-back to BAU governance.
MYDAWA · BOARD BRIEFING · RECOVERY PROGRAMME
08

## Slide 9
WHAT TO EXPECT, MONTH BY MONTH
What 'recovery' looks like, in plain numbers
Two scenarios. The floor assumes only Phase 1 lands. The plan assumes all phases succeed.
Month
Phase
Floor (only Phase 1 lands)
Plan (everything works)
What you're seeing
Month 1
TRIAGE
KES 28.5M
KES 29.0M
Telemetry & checkout in flight; minimal headline movement
Month 2
REBUILD
KES 29.5M
KES 30.5M
Checkout fix landing; first reactivation results
Month 3
REBUILD
KES 30.0M
KES 31.0M
Marketing rebuild compounding; conversion climbing
Month 4
REBUILD
KES 30.5M
KES 32.0M
Plan target hit if all tracks line up
Month 5
DURABLE
KES 30.5M
KES 32.5M
First sustained month at target — the proof
Month 6
DURABLE
KES 31.0M
KES 33.0M
Second sustained month — declared success
If the plan target is not bending upward by Month 3, that is the early warning. The COO surfaces it before Month 4 closes.
MYDAWA · BOARD BRIEFING · RECOVERY PROGRAMME
09

## Slide 10
WHEN TO CHALLENGE THE PLAN
Two moments where we stop and reconsider — written in upfront
Stop conditions are not planning to fail. They are the discipline that prevents a plan from quietly extending past honesty.
DAY 30
If checkout has not moved AND telemetry is clean
THE TEST
By end of Month 1, two things should be true: the cart-to-order conversion has improved, and we trust our funnel data.
IF THE TRIGGER DOES NOT FIRE
If checkout has improved, OR if the data still needs work — we proceed normally.
(Action 1 fix is landing; Action 2 is still confirming the metric.)
IF THE TRIGGER FIRES
If checkout has not moved AND we trust the data showing it — the original diagnosis was wrong.
The COO returns to the board with a revised diagnosis before Phase 2 begins. We do not start the larger investment cycle on a diagnosis we no longer believe.
DAY 120
If revenue has not moved by end of Phase 2
THE TEST
By end of Month 4, the headline KPI — monthly revenue — should have started moving toward target.
IF THE TRIGGER DOES NOT FIRE
If revenue has started moving toward target — we proceed to Phase 3 (durable state).
(Two consecutive months at or above target = success.)
IF THE TRIGGER FIRES
If revenue has not moved, the recovery is not landing.
The COO returns to the board with a Phase 2 review. Phase 3 does not silently start. We either re-scope the recovery or accept a different definition of success.
MYDAWA · BOARD BRIEFING · RECOVERY PROGRAMME
10

## Slide 11
WHAT WE NEED FROM YOU
Three decisions today. Three commitments going forward.
If we cannot get all six, we should pause and renegotiate the plan before starting.
DECISIONS TODAY
Three things we need approved before we start.
1
Approve the diagnosis
The contraction is funnel-led. Checkout, traffic and acquisition are the three things to fix — in that order.
2
Approve the plan and named owners
Eight workstreams, three phases, six months. Single accountable owner per workstream. The COO chairs the programme.
3
Approve the stop conditions
Day 30 and Day 120 are formal review points. The COO comes back if either fires. The plan does not silently extend.
COMMITMENTS GOING FORWARD
Three behaviours we ask the board to hold itself to.
A
Show up to the monthly review
90 minutes a month. The discipline of monthly conversation is what keeps a plan honest. Skipped reviews are how recoveries silently stall.
B
Trust the lead indicators
Revenue is a lag indicator. Cart→order, conversion rate, and new customers will move first. Don't ask for revenue updates in week 4 — ask for the lead numbers.
C
Honour the stop conditions
If they fire, we want to hear 'come back with the revised plan,' not 'push through and report back next quarter.' The whole architecture relies on this.
MYDAWA · BOARD BRIEFING · RECOVERY PROGRAMME
11

## Slide 12
WHAT COULD GO WRONG
Five things that could derail this — and what we'd do
We've named these in advance so the board recognises them when they appear, rather than treating them as surprises.
If checkout is harder to fix than we think
Some checkout problems are quick (fraud-rejection settings, login flow). Others are deep platform debt that takes months. If we find the second kind, Phase 1 extends and the revenue path slides right. We would surface this in the Day 14 milestone review.
If the data tells a different story than we think
The 7% checkout figure is unusually low. If our funnel data turns out to have a measurement bug, we may discover the problem is smaller than thought. Good news in one sense — but our diagnosis would shift, and the recovery plan with it.
If marketing spend was deliberately cut, not just declined
Spend reconstruction in Month 2 will tell us whether the traffic decline is something to fix or a strategic decision the board already made. If the latter, this becomes a board-level conversation about strategy, not a marketing project.
If the loyalty base starts cracking
Our 19,000 loyal customers held us up through 2024. If they begin to lapse during the recovery period, the floor falls out. We watch their retention rate weekly as a tripwire.
If the macro environment shifts
If Kenyan retail more broadly contracts — a possibility that this analysis cannot test — some of the recovery upside disappears. The plan is robust to a portion of this; if the shift is severe, we revise.
MYDAWA · BOARD BRIEFING · RECOVERY PROGRAMME
12

## Slide 13
MYDAWA · RECOVERY PROGRAMME
What we know. What we'll do. What you'll see.
We know why revenue slowed: the digital funnel broke. We know what to do about it: fix the checkout first, then rebuild acquisition, then prove the gain holds. We know how to tell if it's working: three lead indicators move before revenue does.
Six months. One headline number. Three lead indicators. Eight workstreams. Two stop conditions. And a meeting cadence — daily, weekly, monthly, quarterly — that keeps the conversation honest.
Board Briefing · Diagnosis · Plan · Cadence · For approval and ongoing reference